## Sheet1
Feature | Category | Story ID | Title | User Story | Description (AI-Agent Context) | Scope | Deliverables | Acceptance Criteria | Validation Approach | Story Points | Tags
P0 Foundation | AI Context | P0-1A | Define System Prompt for AI Agents Governing Observability Platform Development | As a Data Engineering team, I want a clearly defined system prompt for AI agents so that all AI-generated outputs align with platform architecture | Create primary system prompt defining platform purpose, architecture, constraints, and AI behavior | Define platform vision, architecture, constraints | system-prompt.md | Prompt created and usable by AI agents | Generate sample output | 1 | P0,AI,Context,Foundation,LLM,Architecture
P0 Foundation | AI Context | P0-1B | Define AI Agent Instruction Guidelines for Observability Platform Development | As a Data Engineering team, I want structured AI instructions so that AI generates consistent outputs | Define operational instructions for AI agents including structure and artifacts | Define output structure and artifacts | agent-instructions.md | Instructions produce consistent outputs | Generate sample module | 1 | P0,AI,Instructions,LLM,Standards
P0 Foundation | AI Context | P0-1C | Define Engineering Principles for Modular Observability Platform | As a Data Engineering team, I want engineering principles so that platform follows consistent standards | Define modularity, contract-first design, extensibility principles | Define principles for design and integration | engineering-principles.md | Principles applicable across modules | Review sample modules | 1 | P0,Architecture,Principles,Design
P0 Foundation | AI Context | P0-1D | Define Observability Context Model Including Multi-Layer Telemetry | As a Data Engineering team, I want a well-defined observability model so that telemetry is consistent | Define multi-layer telemetry and collector-based integration | Define telemetry layers and attributes | observability-context.md | Multi-layer telemetry supported | Validate pipeline telemetry | 1 | P0,Observability,Telemetry,Data,Context
P0 Foundation | Repo & Modules | P0-2A | Define Standard Repository Structure for Observability Platform | As a Data Engineering team, I want a standard repo structure so that components are organized consistently | Define base repository layout for platform and modules | Define directories and structure | Repo structure doc | Structure reusable across modules | Create sample repo | 1 | P0,Repo,Structure,Standards
P0 Foundation | Repo & Modules | P0-2B | Define Module Directory Structure and Required Artifacts | As a Data Engineering team, I want a standard module structure so that modules are consistent | Define module folder structure and required artifacts | Define folders and files | Module structure spec | All modules follow structure | Validate sample module | 1 | P0,Modules,Structure,Standardization
P0 Foundation | Repo & Modules | P0-2C | Define Module Metadata Schema (module.yaml) | As a Data Engineering team, I want metadata schema so modules can be discovered | Define schema for module metadata | Define metadata fields | module.yaml schema | Schema usable across modules | Validate metadata | 1 | P0,Metadata,Modules,Schema
P0 Foundation | Repo & Modules | P0-2D | Define Integration Documentation Standard (integration.md) | As a Data Engineering team, I want standard integration docs so interactions are clear | Define integration.md structure | Define sections for integration | integration.md template | Template reusable | Validate sample module | 1 | P0,Documentation,Integration
P0 Foundation | Repo & Modules | P0-2E | Define Context Documentation Standard (context.md) | As a Data Engineering team, I want context docs so modules explain purpose clearly | Define context.md structure | Define sections for purpose | context.md template | Template consistent | Validate module | 1 | P0,Documentation,Context
P0 Foundation | Contracts | P0-3A | Define Telemetry Contract Schema for Logs, Metrics, and Traces | As a Data Engineering team, I want a telemetry contract so data is consistent | Define schema for logs, metrics, traces with extensibility | Define required fields and attributes | Telemetry contract schema | Schema supports all layers | Validate telemetry | 1 | P0,Contracts,Telemetry,Schema
P0 Foundation | Contracts | P0-3B | Define Integration Contract for Module-to-Platform Interaction | As a Data Engineering team, I want integration contract so modules interact consistently | Define module interaction rules via contracts | Define interaction rules | Integration contract | No direct coupling | Validate integration | 1 | P0,Contracts,Integration
P0 Foundation | Contracts | P0-3C | Define Configuration Contract for Platform and Modules | As a Data Engineering team, I want config standard so modules are configurable | Define config schema and hierarchy | Define config patterns | Config contract schema | Config reusable across modules | Validate config | 1 | P0,Contracts,Config
P0 Foundation | Contracts | P0-3D | Define Module Contract Covering Structure and Lifecycle | As a Data Engineering team, I want module contract so lifecycle is consistent | Define lifecycle and versioning rules | Define lifecycle stages | Module contract doc | Modules follow lifecycle | Validate lifecycle | 1 | P0,Contracts,Modules,Lifecycle
P0 Foundation | Contracts | P0-3E | Define Aperture Contract for Platform Entry and Exit Points | As a Data Engineering team, I want aperture contract so all interactions are standardized | Define ingestion and output interfaces | Define platform entry points | Aperture contract | All flows via apertures | Validate flows | 1 | P0,Contracts,Aperture,Architecture
P0 Foundation | Contracts | P0-3F | Establish Contract Validation Rules for CI/CD Enforcement | As a Data Engineering team, I want validation rules so compliance is enforced | Define CI validation rules for contracts | Define validation checks | Validation rules config | Pipeline blocks violations | Test invalid case | 1 | P0,Contracts,Validation,CI
P0 Foundation | CI/CD & Security | P0-4A | Define Standard CI/CD Pipeline Template for Observability Platform | As a Data Engineering team, I want CI/CD template so validation is consistent | Define base CI/CD pipeline with stages | Define pipeline stages | CI/CD template | Template reusable | Apply to module | 1 | P0,CI,Pipeline,DevOps
P0 Foundation | CI/CD & Security | P0-4B | Implement Code Quality and Static Analysis Checks in CI Pipeline | As a Data Engineering team, I want code quality checks so standards are enforced | Integrate linting and static analysis | Define rules and thresholds | CI quality config | Pipeline fails on violations | Test bad code | 1 | P0,CI,Quality,StaticAnalysis
P0 Foundation | CI/CD & Security | P0-4C | Integrate Security Scanning and Dependency Validation in CI Pipeline | As a Data Engineering team, I want security checks so vulnerabilities are prevented | Integrate SAST and dependency scanning | Define tools and thresholds | CI security config | Pipeline blocks vulnerabilities | Test vulnerable dependency | 1 | P0,Security,SAST,CI
P0 Foundation | CI/CD & Security | P0-4D | Define Build and Versioning Strategy for Platform Components | As a Data Engineering team, I want versioning strategy so builds are traceable | Define versioning and tagging rules | Define semantic versioning | Versioning doc | Builds follow versioning | Validate build | 1 | P0,Versioning,Release
P0 Foundation | CI/CD & Security | P0-4E | Enforce Contract Validation as Mandatory CI/CD Gate | As a Data Engineering team, I want contract validation enforced so compliance is ensured | Integrate validation in CI pipeline | Define enforcement stage | CI validation stage | Pipeline blocks violations | Test invalid contract | 1 | P0,CI,Contracts,Enforcement
P0 Foundation | CI/CD & Security | P0-4F | Define Secure Configuration and Secrets Management Approach | As a Data Engineering team, I want secure config handling so data is protected | Define secrets and config handling practices | Define storage and access | Security guidelines | No secrets in code | Validate config | 1 | P0,Security,Secrets,Config
P0 Foundation | Inner Sourcing & Governance | P0-5A | Define Inner Sourcing Contribution Model for Observability Platform | As a Data Engineering team, I want a contribution model so that new modules and enhancements can be safely added by different teams | Define contribution workflow including PR process, review expectations, and integration rules to enable inner sourcing without breaking platform standards | Define contribution workflow, PR lifecycle, ownership model | Contribution guidelines document | Contribution flow clearly defined and usable | Simulate contribution flow with sample module | 1 | P0,InnerSource,Contribution,Governance
P0 Foundation | Inner Sourcing & Governance | P0-5B | Define Module Certification Criteria for Platform Integration | As a Data Engineering team, I want certification criteria so that only compliant modules are integrated into the platform | Define criteria that every module must satisfy before integration including contracts, CI/CD, security, and structure compliance | Define certification checklist and validation criteria | Certification checklist document | Criteria clearly defined and enforceable | Validate with sample compliant/non-compliant modules | 1 | P0,Certification,Modules,Governance
P0 Foundation | Inner Sourcing & Governance | P0-5C | Implement Module Certification Workflow Integrated with CI/CD | As a Data Engineering team, I want an automated certification workflow so that module validation is enforced before integration | Define and integrate certification workflow into CI/CD pipelines ensuring modules pass all required checks before merge | Define certification pipeline stages and checks | CI/CD certification workflow config | Modules cannot merge without certification | Run pipeline with failing module | 1 | P0,CI,Certification,Automation
P0 Foundation | Inner Sourcing & Governance | P0-5D | Define Version Compatibility and Backward Compatibility Strategy | As a Data Engineering team, I want version compatibility rules so that modules can evolve without breaking existing integrations | Define compatibility strategy for contracts, modules, and configurations ensuring backward compatibility | Define version compatibility rules and upgrade paths | Compatibility strategy document | Backward compatibility rules clearly defined | Validate with version upgrade scenario | 1 | P0,Versioning,Compatibility
P0 Foundation | Inner Sourcing & Governance | P0-5E | Define Module Registry and Discovery Mechanism | As a Data Engineering team, I want a module registry so that available modules can be discovered and reused easily | Define mechanism to register, list, and discover modules along with metadata and capabilities | Define registry structure and metadata requirements | Module registry specification | Modules discoverable via metadata | Validate registry with sample modules | 1 | P0,Registry,Modules,Discovery
P0 Foundation | Inner Sourcing & Governance | P0-5F | Define Governance Model for Platform Standards and Evolution | As a Data Engineering team, I want a governance model so that platform standards evolve in a controlled and consistent manner | Define ownership, decision-making process, and change management for contracts, standards, and architecture | Define governance roles and approval workflows | Governance model document | Governance process clearly defined | Simulate change request workflow | 1 | P0,Governance,Standards,Control